## Sheet1
W/C
| 2020-03-02 | 2020-03-09 | 2020-03-16 | 2020-03-23 | 2020-03-30
Calum
Neill
Jane
Ellie
Thomas
Deadlines: | High-Level Plan - 02/03
Requirements Gathering - 09/03
Use Case Diagram - 09/03
Low-Fidelity Prototype - 09/03
Revised Project Plan - 09/03

## Sheet2
Name/Temporary Roles
Date | Milestone | Calum | Neill | Jane | Ellie | Thomas
|  | Developer | Product Owner | Market Researcher | Market Researcher | Product Owner
2020-03-02 | Project Plan, Questionaire Issue | Prototype | Use Cases | Market Research | Market Research | Use Cases
2020-03-03 |  | Prototype | Use Cases | Market Research | Market Research | Use Cases
2020-03-04 |  | Prototype | Use Cases | Market Research | Market Research | Use Cases
2020-03-05 |  | Prototype | Use Cases | Market Research | Market Research | Use Cases
2020-03-06 | Questionaire Processing | Prototype | Use Cases | Market Research | Market Research | Use Cases
2020-03-07 |  | Prototype | Use Cases | Market Research | Market Research | Use Cases
2020-03-08 |  | Prototype | Use Cases | Market Research | Market Research | Use Cases
2020-03-09 | Requirements Gathering, Use Case Diagram, Low-Fidelity Prototype, Revised Plan | TBC | TBC | TBC | TBC | TBC
2020-03-10
2020-03-11
2020-03-12 | Evidence of User Centred Usability Test, Evidence of a Variety of Techniques
2020-03-13
2020-03-14
2020-03-15 | Medium-Fidelity Prototype
2020-03-16
2020-03-17
2020-03-18
2020-03-19 | Evidence of User Centred Usability Test, Evidence of a Variety of Techniques
2020-03-20
2020-03-21
2020-03-22
2020-03-23 | High-Fidelity Prototype
2020-03-24
2020-03-25
2020-03-26
2020-03-27
2020-03-28
2020-03-29
2020-03-30 | Final Prototype
2020-03-31 | Demo
2020-04-01
2020-04-02
2020-04-03
2020-04-04
2020-04-05